## Score table
Area | Stated | Assessed | Crosswalk (ISO/IEC 19770-1 · COBIT 2019 · ISO 27001) | Reasoning
governance | 3 | 3 Unverified: | XW-003 (4.3, 5.2 · APO01 · A.5.1), XW-004 (5.3 · APO01 · A.5.2) | No policy was supplied. council-draft.md has a scope but no decision rights, quorum or sponsor, which fits 3 at best.
inventory | 3 | 3 Unverified: | XW-001, XW-005 (8.3 · BAI09.01 · A.5.9) | 60 apps are recorded with every field filled in. No discovery or reconcile date is given.
entitlement | 1 | 1 | XW-006/007/008 (8.4 · BAI09.05 · A.5.32) | The data supports this score. Two licenses have expired but the apps are still in use (details below). For 41 of 60 apps, recorded users exceed entitlements.
lifecycle | 2 | 2 | XW-009 (19770-1 Annex A · BAI09.03 · A.5.9), XW-010 (19770-1 Annex A Retirement · BAI09.03 · A.8.10). | The data doesn't contradict this. Apps keep running after their licenses lapse, and there's no retirement trail.
vendor | 4 | 4 Unverified: | XW-013 (8.7 · APO10 · A.5.19, A.5.20) | Renewal dates are on file. No vendor risk ratings are supplied, so I can't confirm the "Measured" level.
data-quality | 1 | 1 | XW-026 (8.3 · BAI09.01 · A.5.9) | The data supports this score. Account ACC-104 belongs to EMP-099, who isn't in the employee records. Five categories each have two overlapping products that nobody has reconciled.
security | 3 | 3 Unverified: | XW-014 (DSS05.04 · A.5.15) | Held at 3, with a serious related finding (see below).
cost | 4 | 4 Unverified: | XW-012 (APO06) | No budget-versus-actual data was supplied.
reporting | 3 | 3 Unverified: | XW-025 (9.1–9.3, 10.3 · MEA01 · 9.1, 10.1) | No metrics pack or review action was supplied.

## 90-day plan
Gap | Proposed owner role | Actions (days 0–90) | Evidence of progress
entitlement | Software asset / license manager | 1. Resolve LIC-017 and LIC-044 within 30 days (renew or shut down). 2. Build a compliance position for the top 10 apps by cost, comparing entitlements to actual installs and seats (XW-007). 3. Set up renewal alerts 90 days before every expiry (XW-008). | A dated compliance position for the top 10 apps, no expired licenses on live apps, and a renewal calendar.
data-quality | ITAM manager (with the HR data owner) | 1. Set the required fields and a monthly 10-record sample check. 2. Reconcile all accounts against the HR employee records. Fix or remove ACC-104 and any other account with no matching employee. 3. Review the 5 overlapping category pairs and record a keep/merge decision for each. | Sample accuracy rising month on month, zero accounts without a matching employee, and a decision log for the 5 pairs.
lifecycle | Application portfolio owner | 1. Document the path from request to approval, renewal and retirement (XW-009). 2. Add a decommissioning checklist covering data removal and access removal (XW-010). 3. Run one real retirement through it, for example a loser from the overlap review. | An approved process document and one retirement with its full audit trail.